DHOBIGHAT

Laundry Management Platform

PROJECT PLAN & SPRINT ROADMAP

Version 1.0  |  May 2026

# 1. Project Overview

Execution plan for DhobiGhat v1.0 — a full-featured laundry platform. Covers 6 sprints across 12 weeks: 5 sprints for core platform + 1 sprint dedicated to the full customer app (browse, discovery, favourites, rich home, reviews, collection confirmation).

| Parameter | Value |
| --- | --- |
| Development model | AI writes code per task. Owner reviews and tests each task before moving on. |
| Project start | Week of June 2, 2026 |
| Target launch | Week of August 25, 2026 (12 weeks) |
| Sprints | 6 sprints × 2 weeks each |
| Team | Solo owner + Claude (AI) for code generation |
| Repos | dhobighat-api, dhobighat-washerman-app, dhobighat-customer-app |
| Mobile | Expo EAS — Android + iOS |
| Backend | Render (auto-deploy from main) |
| Database | Neon serverless Postgres (free tier) |
| Monitoring | Grafana + Loki (self-hosted on Render) |

# 2. AI-Assisted Development Workflow

| Step | Who | Action |
| --- | --- | --- |
| 1 | Owner | Open Claude. Paste task ID + description + relevant schema/code context. |
| 2 | Claude | Generate full module: migration, route, controller, service, validation, tests. |
| 3 | Owner | Copy code into repo. Run migrations. Start server. Read through the code. |
| 4 | Owner | Run manual QA checklist for that task. Happy path + edge cases. |
| 5 | Owner + Claude | Fix issues found. Iterate until task passes. |
| 6 | Owner | Merge to main. Move to next task. |

# 3. Sprint Plan Summary

| Sprint | Weeks | Focus | Key Deliverables |
| --- | --- | --- | --- |
| Sprint 1 | 1–2 | Foundation | Repo setup, all DB migrations (incl. reviews, favourites), Auth (Twilio + JWT), Washerman + Customer registration APIs, Expo app shells, Render + Neon deploy |
| Sprint 2 | 3–4 | Pricing + Orders | Price grid CRUD (item × wash type), Order creation with itemized preview, FCM push on new order, Washerman accept/decline queue, Customer order screens |
| Sprint 3 | 5–6 | Status + Collection | Full order lifecycle, double collection confirmation (washerman + customer independently), order cancellation rules, notification inbox, order tracking timeline UI |
| Sprint 4 | 7–8 | Customer App — Discovery | Browse + filter washermen API + UI, Washerman public profile, Washerman selection/switching, Favourites (add/remove/list), Reviews (submit + display), Washerman availability toggle + display, Rich home screen |
| Sprint 5 | 9–10 | Accounting + PDF | Accounting summary + ledger APIs, Mark as paid, PDFKit receipt + statement, Accounting screens (both apps), Date range filters, PDF download |
| Sprint 6 | 11–12 | Polish + Launch | Full E2E QA on all flows, security audit, Grafana + Loki setup, Expo EAS production builds, Play Store + App Store submission, 10 real washermen + 30 customers onboarded |

# 4. Sprint Details — AI-Ready Task Breakdown

## Sprint 1 — Foundation (Weeks 1–2)

| # | Task (AI Coding Session) | Test / Review Criteria |
| --- | --- | --- |
| 1.1 | Initialize Express.js project: folder structure, Knex config, Zod, error handler, health check (/health) | GET /health → 200. Knex connects to Neon. |
| 1.2 | All DB migrations: washermen (with area, avg_rating, review_count, is_available), customers (selected_washerman_id), favourites, wash_types, price_items, price_grid, orders (with all new status enums, washerman_collected_at, customer_collected_at), order_items, reviews, notifications | knex migrate:latest clean. All tables with correct columns, constraints, enums. |
| 1.3 | Auth — OTP request: Twilio Verify integration, rate limiting 3/hour/phone | OTP SMS received. 4th request rejected with 429. |
| 1.4 | Auth — OTP verify: Twilio verify check, issue JWT access (15min) + refresh (30 days, hashed) | Correct OTP → tokens. Wrong → 401. Expired → 401. |
| 1.5 | Auth middleware: JWT verify, role attach, protected route guard | No token → 401. Wrong role → 403. |
| 1.6 | Washerman registration API: name, business_name, area, address. Auto-generate unique_code. | Registration works. Unique code generated. Duplicate phone → 409. |
| 1.7 | Customer registration API: name, address. selected_washerman_id nullable (can browse first). | Registration works. selected_washerman_id null until customer selects one. |
| 1.8 | Expo washerman app: project init, tab navigation (Home, Orders, Accounting, Profile), auth screens, secure token storage | App runs on Android + iOS simulator. Auth flow complete. Tokens stored. |
| 1.9 | Expo customer app: project init, navigation (Home, Browse, Orders, Favourites, Accounting, Profile), auth screens | Customer app runs. Auth flow complete. |
| 1.10 | Deploy API to Render. Connect Neon. Set env vars. Verify /health on live URL. | Production /health → 200. Auth endpoints work on production. |

## Sprint 2 — Pricing + Orders (Weeks 3–4)

| # | Task (AI Coding Session) | Test / Review Criteria |
| --- | --- | --- |
| 2.1 | Pricing API — items: POST/PUT /pricing/items. Seed defaults: shirt, pant, saree, kurta, bedsheet, towel. | Washerman adds item. Customer gets 403. Deactivated item absent from grid. |
| 2.2 | Pricing API — wash types: POST/PUT /pricing/wash-types. Seed defaults: Normal Wash, Dry Clean, Steam Press. | Washerman adds wash type. Deactivated type hidden from grid. |
| 2.3 | Pricing API — grid: PUT /pricing/grid/:item_id/:wash_type_id. GET /pricing/grid returns nested structure. Public access via ?washerman_id= | Price set for Shirt + Dry Clean. Grid correct. Customer can read, not write. |
| 2.4 | Washerman app: Price grid management screen. Item × wash type table. Price input per cell. | Washerman sets prices. Saves to API. Grid reloads with correct values. |
| 2.5 | Order creation API: validate items exist in price_grid. Calculate total. Store price snapshots. Set delivery_mode. | Order created with correct total. Snapshots stored. Delivery mode saved. |
| 2.6 | FCM push on new order to washerman's FCM token. Store notification in DB. | Washerman push within 5 seconds of order. Notification row in DB. |
| 2.7 | Order list API: GET /orders. Role-aware. Filters: ?status= ?delivery_mode= ?from= ?to= ?page= | Washerman sees all, customer sees own. Filters correct. |
| 2.8 | Order status API — accept/decline: PATCH /orders/:id/status. Washerman only. State machine: pending → accepted or declined. | Accept works. Decline stores reason. Invalid transition → 422. |
| 2.9 | Customer app — order creation: price grid display, item + wash type picker, quantity, real-time subtotal per line, grand total, delivery mode, pickup date, review screen before submit. | Correct total shown before submit. API called on confirm. Order in history. |
| 2.10 | Washerman app — order queue: pending orders list on home. Each card shows customer, items, delivery mode, total, date. Accept/decline buttons with reason input. | Pending orders listed. Accept/decline works. Decline reason saved. |

## Sprint 3 — Status, Collection & Notifications (Weeks 5–6)

| # | Task (AI Coding Session) | Test / Review Criteria |
| --- | --- | --- |
| 3.1 | Order cancellation API: PATCH /orders/:id/cancel. Customer only. Allowed if status = pending or accepted (and washerman_collected_at IS NULL). Sets status = cancelled. Pushes washerman. | Cancel from pending works. Cancel from accepted-not-collecting works. Cancel attempt after COLLECTING → 422. |
| 3.2 | Collection confirmation API: PATCH /orders/:id/confirm-collection. Role-aware. Sets washerman_collected_at or customer_collected_at. Moves to COLLECTED only when both set. | Washerman confirms → stays COLLECTING. Customer confirms → COLLECTED. Both notified. |
| 3.3 | Collection reminder cron: if status = COLLECTING and customer_collected_at NULL after 2 hours, send push to customer. | Customer receives reminder push after 2-hour window. |
| 3.4 | Order status API — full lifecycle: COLLECTING → COLLECTED → IN_PROGRESS → READY → DELIVERED. Washerman only (except confirm-collection). | Full progression works. Each step triggers customer push. Invalid transitions rejected. |
| 3.5 | Drop-off order shortcut: when delivery_mode = drop_off, ACCEPTED jumps directly to IN_PROGRESS (skip COLLECTING and COLLECTED). | Drop-off order: accepted → in_progress works. COLLECTING not applicable. |
| 3.6 | Notification API: GET /notifications, PATCH /:id/read, PATCH /read-all. Role-aware. | Inbox returns correct notifications. Mark-read works. Unread count accurate. |
| 3.7 | Washerman app — active orders: status update buttons per order. Collecting → In Progress → Ready → Delivered. Confirm dialog before each change. | Status progression works from washerman side. Each step pushes customer. |
| 3.8 | Customer app — order detail: status timeline (step indicator), decline reason display, Cancel button (visible when cancellable), Confirm Collection button (visible when COLLECTING). | Timeline accurate. Cancel visible/hidden correctly. Collection confirm works. |
| 3.9 | Both apps — notification inbox: unread badge on tab, list of notifications, mark read on open, tap to navigate to order. | Badge shows count. Tap navigates. Badge clears after read. |
| 3.10 | Both apps — empty, loading, error states for all screens. Offline banner. | Empty states have helpful copy. Retry on error. Offline banner appears without internet. |

## Sprint 4 — Customer App: Discovery, Browse & Rich Home (Weeks 7–8)

| # | Task (AI Coding Session) | Test / Review Criteria |
| --- | --- | --- |
| 4.1 | Browse API: GET /washermen. Filters: ?area= &min_rating= &max_price_paise= &available_only=true &page= &limit=. Returns: name, area, avg_rating, review_count, is_available, starting_price_paise. | All filters work independently and combined. Unavailable washermen hidden when available_only=true. Pagination correct. |
| 4.2 | Washerman public profile API: GET /washermen/:id. Returns full profile + price grid + recent reviews. | Profile returns correct data. Price grid structured correctly. Reviews included. |
| 4.3 | Washerman availability toggle API: PATCH /washermen/me/availability { is_available: bool }. Washerman only. | Toggle works. Reflected in browse results immediately. |
| 4.4 | Washerman selection/switch API: PUT /customers/me/washerman { washerman_id }. Updates selected_washerman_id. Returns new washerman profile. | Switch works. New washerman reflected in customer profile. Old orders unaffected. |
| 4.5 | Favourites API: GET /customers/me/favourites, POST /customers/me/favourites/:id, DELETE /customers/me/favourites/:id. | Add/remove/list all work. Duplicate add returns 409 or idempotent. |
| 4.6 | Reviews API: POST /reviews { order_id, rating, review_text }. Validate order delivered + customer owns it + no prior review. Trigger update washermen.avg_rating + review_count. | Review saved. Washerman avg_rating updated. Duplicate review → 409. Non-delivered order → 422. |
| 4.7 | Reviews list API: GET /washermen/:id/reviews. Paginated. Returns customer name, rating, review_text, created_at. | Reviews listed for washerman. Pagination works. |
| 4.8 | Customer app — Browse screen: washerman cards (name, area, rating stars, review count, availability badge, starting price). Filter bar (area, min rating, max price, available only). | Cards render correctly. Filters update list. Available-only hides closed washermen. |
| 4.9 | Customer app — Washerman profile screen: full info, price grid table, availability status, rating, reviews list, Select This Washerman button, Favourite toggle. | All data renders. Select button updates selected washerman. Favourite toggle works. |
| 4.10 | Customer app — Favourites tab: list of favourited washermen. Tap to view profile. Remove button. | Favourites list loads. Tap navigates to profile. Remove works. |
| 4.11 | Washerman app — availability toggle: switch on home screen. Shows current status. Toggle sends PATCH to API. | Toggle updates availability. Status reflected in customer browse. |
| 4.12 | Customer app — Rich home screen: (1) Active order card with live status. (2) Quick new order button. (3) Selected washerman spotlight (name, rating, availability). (4) Favourites horizontal strip. (5) Care tips section (static cards: silk care, cotton care, wool storage, stain removal). | All sections render. Active order card shows correct status. Tips are tappable with full guide text. |
| 4.13 | Customer app — Post-delivery review prompt: after order moves to DELIVERED, prompt appears on order detail screen with star picker and optional text input. | Prompt appears after delivered. Review submits. Prompt hidden after submission or dismissal. |

## Sprint 5 — Accounting & PDF (Weeks 9–10)

| # | Task (AI Coding Session) | Test / Review Criteria |
| --- | --- | --- |
| 5.1 | Accounting summary API: GET /accounting/summary. Role-aware. Washerman: total_revenue_paise, outstanding_paise, order counts. Customer: total_spent_paise, current_due_paise. Supports ?from= ?to= | Figures match manual calculation. Date range filters correctly. |
| 5.2 | Accounting ledger API: GET /accounting/ledger. Washerman: per-customer (billed, paid, due). Customer: per-order breakdown. | Per-row figures accurate. Totals match summary. |
| 5.3 | Mark as paid API: PATCH /orders/:id/payment { is_paid: true }. Washerman only. Sets paid_at. Pushes customer. | Paid flag set. paid_at recorded. Outstanding balance drops in summary. Customer push received. |
| 5.4 | PDF — order receipt: PDFKit template. DhobiGhat header, washerman business name, order number, date, delivery mode, items table (item, wash type, qty, unit price, subtotal), grand total, payment status. | PDF correct. All data present. Downloads under 3 seconds. |
| 5.5 | PDF — account statement: date range header, all orders in period, per-order rows, running balance, grand total due. | Statement accurate. Running balance correct. Period totals match. |
| 5.6 | PDF export API: GET /accounting/export?type=receipt&order_id= and ?type=statement&from=&to=. Streams PDF with Content-Disposition header. | PDF downloads correctly. Correct filename. Content-Type: application/pdf. |
| 5.7 | Washerman app — accounting dashboard: KPI cards (revenue, outstanding). Customer ledger list. Tap customer for their order history + balance. Mark as paid on order. | KPIs load. Customer drill-down works. Mark as paid reflects immediately. |
| 5.8 | Customer app — accounting screen: KPI cards (spent, due). Per-order list with payment status. | Customer figures correct. All orders listed. Payment status reflects washerman's mark. |
| 5.9 | Both apps — PDF download button: on order detail and accounting screens. Opens native share sheet. | Tapping download opens share sheet with PDF. File saveable. |
| 5.10 | Both apps — date range picker for accounting: this week / this month / custom. | Selecting range reloads data correctly. Custom range picker works. |

## Sprint 6 — Polish & Launch (Weeks 11–12)

| # | Task (AI Coding Session) | Test / Review Criteria |
| --- | --- | --- |
| 6.1 | Run full manual QA checklist (Section 7) on real Android + iOS devices. Document all bugs with severity. | All checklist flows completed. Bugs documented with P0/P1/P2 labels. |
| 6.2 | Fix all P0 bugs: crashes, wrong totals, broken auth, failed pushes, broken collection flow. | Zero P0 bugs on retest. |
| 6.3 | Fix all P1 bugs: wrong status transitions, PDF errors, broken filters, review submission issues. | Zero P1 bugs on retest. |
| 6.4 | Security audit: JWT expiry, rate limits active, HTTPS enforced, no secrets in logs or code, all queries parameterized, role checks on every endpoint. | Security checklist complete. No exposed secrets. All role checks pass. |
| 6.5 | Set up Grafana + Loki on Render. Configure structured JSON logging from Express. Dashboard: request rate, error rate, slow queries. Alert: 5xx > 5% for 5 minutes. | Logs visible in Loki. Dashboard live. Alert fires on test 5xx spike. |
| 6.6 | Production environment: set all env vars on Render production service. Run all migrations on Neon production DB. Verify /health. | Production /health → 200. All migrations applied. |
| 6.7 | Expo EAS: production build profiles for both apps. Build washerman app (Android APK + iOS IPA). Install and test against production API. | Both builds install. All washerman flows work on production. |
| 6.8 | Expo EAS: build customer app (Android + iOS). Install and test all customer flows on production: browse, favourite, order, collection confirm, review, PDF. | All customer flows work on production builds. |
| 6.9 | Submit both apps to Google Play (internal track) and App Store Connect (TestFlight). Prepare store listings. | Submissions accepted. Internal testers can install from store. |
| 6.10 | Onboard 10 real washermen: help them set up profiles, area, price grid, availability. Onboard 30 customers. Run 5 real end-to-end orders. | 10 washermen live. 30 customers registered. 5 completed orders with review submitted. |

# 5. Timeline — Gantt Overview (12 Weeks)

W1 = June 2 → W12 = August 22, 2026. Blue = active.

| Module | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1: Foundation |  |  |  |  |  |  |  |  |  |  |  |  |
| DB Migrations (all tables) |  |  |  |  |  |  |  |  |  |  |  |  |
| Auth (Twilio + JWT) |  |  |  |  |  |  |  |  |  |  |  |  |
| App Shells + Deploy |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 2: Pricing + Orders |  |  |  |  |  |  |  |  |  |  |  |  |
| Price Grid API + UI |  |  |  |  |  |  |  |  |  |  |  |  |
| Order Create + FCM |  |  |  |  |  |  |  |  |  |  |  |  |
| Accept/Decline Queue |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 3: Status + Collection |  |  |  |  |  |  |  |  |  |  |  |  |
| Order Lifecycle + Cancel |  |  |  |  |  |  |  |  |  |  |  |  |
| Double Collection Confirm |  |  |  |  |  |  |  |  |  |  |  |  |
| Notification Inbox + UI |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 4: Customer Discovery |  |  |  |  |  |  |  |  |  |  |  |  |
| Browse + Filter API + UI |  |  |  |  |  |  |  |  |  |  |  |  |
| Favourites + Selection |  |  |  |  |  |  |  |  |  |  |  |  |
| Reviews + Availability |  |  |  |  |  |  |  |  |  |  |  |  |
| Rich Home Screen |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 5: Accounting + PDF |  |  |  |  |  |  |  |  |  |  |  |  |
| Accounting API |  |  |  |  |  |  |  |  |  |  |  |  |
| Accounting Screens |  |  |  |  |  |  |  |  |  |  |  |  |
| PDFKit + Download |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 6: Polish + Launch |  |  |  |  |  |  |  |  |  |  |  |  |
| QA + Bug Fixes |  |  |  |  |  |  |  |  |  |  |  |  |
| Security + Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| EAS Builds + Store Submit |  |  |  |  |  |  |  |  |  |  |  |  |

# 6. Key Milestones

| Milestone | Target Date | Success Criteria |
| --- | --- | --- |
| M1: Auth Live | June 13, 2026 | Washerman + customer register/login via Twilio OTP. Both Expo apps connect to Render. |
| M2: First Order Placed | June 27, 2026 | Customer creates order with item × wash type. Itemized total correct. Washerman receives FCM. Accept/decline works. |
| M3: Collection Confirmed | July 11, 2026 | Full order lifecycle working. Double collection confirmation (both parties). Cancellation before collecting works. |
| M4: Customer Discovery Live | July 25, 2026 | Browse + filter working. Washerman profiles show price grid + reviews. Favourites work. Rich home complete. |
| M5: Accounting + PDF Working | August 8, 2026 | Accounting dashboards accurate. PDFs download correctly. Mark-as-paid works. |
| M6: Production Launch | August 25, 2026 | Both apps on stores. Production API live + monitored. 10 washermen, 30 customers onboarded, 5 real orders completed. |

# 7. Manual QA Checklist

## Authentication

- OTP received within 30 seconds

- Wrong OTP → error, no login

- 3 wrong OTPs → 15-min lockout

- Expired OTP (5 min) → rejected

- Access token expiry → silent refresh

## Pricing

- Washerman adds item → appears in grid

- Washerman sets price for Shirt + Dry Clean → customer sees it in order screen

- Price change → old orders unaffected

- Deactivated item → hidden from customer

## Order Flow

- Itemized breakdown shows correctly before submit

- Grand total matches sum of line subtotals

- Delivery mode saved and visible to washerman

- FCM push to washerman within 5 seconds

- Washerman declines with reason → customer sees reason

- Customer cancels pending order → washerman notified

- Customer cannot cancel after COLLECTING started → Cancel button hidden

## Collection Confirmation

- Washerman marks COLLECTING → customer push received

- Customer confirms → status moves to COLLECTED, both notified

- Only washerman confirms, customer does not → status stays COLLECTING

- Drop-off order: ACCEPTED jumps to IN_PROGRESS, no COLLECTING step

## Browse & Discovery

- Area filter returns only washermen in that area

- Rating filter hides washermen below threshold

- Available-only filter hides closed washermen

- Filters combine correctly

- Washerman profile shows correct price grid and reviews

- Selecting washerman updates home screen spotlight

- Switching washerman requires confirmation and works correctly

- Favouriting a washerman adds them to Favourites tab

## Reviews

- Review prompt appears only after DELIVERED

- Star rating required — cannot submit without it

- Second review on same order → blocked

- Review appears on washerman's public profile

- Washerman avg_rating updates after review

## Accounting & PDF

- Washerman outstanding decreases after mark-as-paid

- Customer due reflects unpaid delivered orders

- Date range filter correct

- PDF receipt: all items, wash types, totals, delivery mode correct

- PDF statement: running balance and period totals accurate

- PDF downloads in under 3 seconds

## Edge Cases

- Order with no items → validation error

- Past pickup date → validation error

- Review on non-delivered order → blocked

- Cancel after COLLECTING started → blocked

- FCM token missing → push fails gracefully, in-app inbox still works

- No internet → offline banner, cached home/orders visible

# 8. v1.1 Backlog

| Pri | Feature | Why | Complexity |
| --- | --- | --- | --- |
| P1 | UPI / Razorpay payment | Cash-only is biggest friction for customers | High — gateway compliance, webhooks |
| P1 | WhatsApp / SMS notification fallback | Washermen without stable internet miss FCM | Medium — Twilio SMS or WA Business |
| P2 | GPS-based washerman discovery | Manual area filter limits accuracy | Medium — expo-location, geofencing |
| P2 | Hindi UI | Expand to non-English users | Medium — i18n library, translation |
| P2 | Washerman reply to reviews | Give washermen a voice on feedback | Low — reply field on review |
| P3 | Pickup time slot selection | Customer picks morning/afternoon/evening | Low — time_slot field on orders |
| P3 | Recurring order templates | Most customers order same items weekly | Low — saved order + quick reorder |
| P3 | Estimated turnaround time on profile | Help customers choose washerman | Low — washerman sets avg days |
| P4 | Admin web dashboard | Owner monitors platform health | High — new web app, admin role |
| P4 | Referral + loyalty system | Organic growth mechanism | Medium — referral codes, points table |